## Sheet1
mega:bit Project Gantt Chart
| week 1 28/04 - 04/05 | week 2 05/05 - 11/05 | week 3 12/05 - 18/05 | week 4 19/05 - 25/05 | week 5 26/05 - 1/06 | week 6 02/06 - 08/06 | week 7 09/06 - 15/06 | week 8 16/06 - 22/06 | week 9 23/06 - 29/06
Background Research | [9 empty] | Legend
Client Meeting | 1st meeting |  | 2nd meeting | 3rd meeting | [5 empty] | General
Primary Research - Survey | [9 empty] | Hardware
Decide on Implementation | [9 empty] | Software
PCB Design |  | 1st revision | 2nd revision |  | 3rd revision |  |  |  |  | Deliverables
Software Design Method Selection
Supervisor Meeting
Software Implementation
PCB Building and Testing
Leaflet Design
Poster Design
Prototype Building and Testing
Client Demonstration | [6 empty] | 15th June
Deadlines
Leaflet | [5 empty] | 9th June
Hackbooth | [6 empty] | 14th June
Documentation/Files | [8 empty] | 27th June
Peer assessment | [8 empty] | 27th June